## Sheet1
Date Reported | Module | Severity Low/Medium/High Cosmetic Security errors have a severity of high. | Fix Planned Y/N | Fix Date | Description
2019-10-10 | IRIS Menu #10 | Cosmetic |  |  | Capitalize "setup" to "Setup" for consistancy
2019-10-10 | IRIS Menu #11 | Cosmetic |  |  | Capitalize "setup" to "Setup" for consistancy
2019-10-10 | IRIS Menu #10 | Cosmetic |  |  | Change "Survey's setup" to "Survey Setup"
2019-10-10 | IRIS Menu #10.2 | Cosmetic |  |  | Change "Survey's Builder" to "Survey Builder"
2019-10-10 | IRIS Top Level Menu Bar | High |  |  | Right arrow to exit, exits. But, appears to re-enter the system by simply clicking on the browser back arrow. Functions won't work but, you get the home page without signing in.
2019-10-10 | IRIS Top Level Menu Bar | High |  |  | Home icon exits. But, appears to re-enter the system by simply clicking on the browser back arrow. Functions won't work but, you get the home page without signing in.
2019-10-10 | IRIS Home Page | Low |  |  | There is a help file, titled "User Manual." It does not appear valid. Is it valid? Or partially valid?
2019-10-10 | IRIS Menu #5 | Cosmetic |  |  | Workshop Sites detail entry screen should have a title like all the other detail entry screens. Standardization error.
2019-10-10 | IRIS Menu #5 | Cosmetic |  |  | Workshop Sites screen should have a title "Workshop Sites" matching the menu title like all the other detail entry screens. Standardization error.
2019-10-17 | IRIS Login | High |  |  | Password reset emails the user's password in the clear. It would be safer to simply ask the user to create a new password.
2019-10-17 | IRIS Menu #12.4 | Cosmetic |  |  | When requesting a forgotten password, the alert box stating an email has been sent, opens up on the top of the screen. The message box should open on top of and centered in the windows already open.
2019-10-17 | IRIS Login | Cosmetic |  |  | Spelling error. The word "again" is mispelled "againg"
2019-10-17 | IRIS Menu #12.4 | Cosmetic |  |  | When making a change to a user, if there is an issue a message box opens up on the top of the screen. The message box should open above and centered in the windows already open.
2019-10-17 | IRIS Menu #12.4 | Cosmetic |  |  | When adding a user, upon completion, a message box opens up to the top left of the screen. The message box should open above and centered in the windows already open.
2019-10-17 | IRIS Menu #12.4 | High |  |  | If I can't create users in different agencies, then why can I see them?
2019-10-17 | IRIS Menu #12.4 | High |  |  | Can create a user without a password
2019-10-17 | IRIS Menu #12.4 | Unknown |  |  | Can not delete a user. The system may want an unalterable history.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Can erase the password from a user's profile and save it successfully.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Can erase the first name from a user's profile and save it successfully.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Can erase the last name from a user's profile and save it successfully.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Can erase the email from a user's profile and save it successfully.
2019-10-17 | IRIS Menu #12.4 | Low |  |  | If an incorrectly formatted email is entered, a message box appears on the top of the screen. The message box should open on top of and centered in the windows already open.
2019-10-17 | IRIS Menu #12.4 | Medium |  |  | An email is not required to have an extenstion. Ex. ".com"
2019-10-17 | IRIS Menu #12.4 | Unknown |  |  | Can create two users with the same email. This may be acceptable for couples.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Two users can have the same first and last name.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Can create duplicate users
2019-10-17 | IRIS Menu #12.4 | High |  |  | Can erase the password from a coordinator 's profile and save it successfully.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Can erase the first name from a coordinator 's profile and save it successfully.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Can erase the last name from a coordinator 's profile and save it successfully.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Can erase the email from a coordinator 's profile and save it successfully.
2019-10-17 | IRIS Menu #12.4 | Low |  |  | If an incorrectly formatted email is entered, a message box appears on the top of the screen. The message box should open on top of and centered in the windows already open.
2019-10-17 | IRIS Menu #12.4 | Medium |  |  | An email is not required to have an extenstion. Ex. ".com"
2019-10-17 | IRIS Menu #12.4 | Unknown |  |  | Can create two coordinator s with the same email. This may be acceptable for couples.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Two coordinator s can have the same first and last name.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Can create duplicate coordinator s
2019-10-17 | IRIS Menu #12.4 | Cosmetic |  |  | When adding a coordinator , upon completion, a message box opens up to the top left of the screen. The message box should open above and centered in the windows already open.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Can erase the password from a manager's profile and save it successfully.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Can erase the first name from a manager's profile and save it successfully.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Can erase the last name from a manager's profile and save it successfully.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Can erase the email from a manager's profile and save it successfully.
2019-10-17 | IRIS Menu #12.4 | Low |  |  | If an incorrectly formatted email is entered, a message box appears on the top of the screen. The message box should open on top of and centered in the windows already open.
2019-10-17 | IRIS Menu #12.4 | Medium |  |  | An email is not required to have an extenstion. Ex. ".com"
2019-10-17 | IRIS Menu #12.4 | Unknown |  |  | Can create two managers with the same email. This may be acceptable for couples.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Two managers can have the same first and last name.
2019-10-17 | IRIS Menu #12.4 | High |  |  | Can create duplicate managers
2019-10-17 | IRIS Menu #12.4 | Cosmetic |  |  | When adding a manager, upon completion, a message box opens up to the top left of the screen. The message box should open above and centered in the windows already open.
2019-10-17 | IRIS Menu #12.3 | High |  |  | The roles do not seem to have any effect. Access to a function is permitted even if not allowed.
2019-10-17 | IRIS Menu #12.3 | High |  |  | The roles do not seem to have any effect. Access to a function is permitted even if not allowed. Data can displayed.
2019-10-17 | IRIS Menu #12.3 | High |  |  | The roles do not seem to have any effect. Any user can escalate rights even if they do not have access to administration.
2019-10-17 | IRIS Menu #12.3 | Medium |  |  | When a new user role is created, it does not appear in the table of user roles, even if filters are cleared. One must exit the "User Roles" function and re-enter the function for the new role to appear.
2019-10-17 | IRIS Menu #12.3 | Medium |  |  | If adding a role and no agency is selected, the message "Data Saved" appears and it looks like the new role was created. But, it is not in the table. If it is entered as garbage into the file, I can not see.
2019-10-17 | IRIS Menu #12.1 | High |  |  | Duplicate agencies with same name and region allowed.
2019-10-24 | IRIS Menu #1 | Medium |  |  | Can not enter a funding source in the textbox for funding source, to do a search
2019-10-24 | IRIS Menu #1 | Medium |  |  | Can not create a funding source once any action has been taken within the funding source window. Can only enter a new funding source when first entering the funding source window.
2019-10-24 | IRIS Menu #1 | Medium |  |  | Budget amount zeroes out if entered with funding source creation.
2019-10-24 | IRIS Menu #1 | Medium |  |  | Budget amount must be at least one dollar
2019-10-24 | IRIS Menu #1 | Medium |  |  | Budget amount can not have pennies.
2019-10-24 | IRIS Menu #1 | Medium |  |  | Budget amount limited to 999,999.00
2019-10-24 | IRIS Menu #1 | Medium |  |  | If a budget of one million is entered, the amount is converted to thousands. One million = 1,000 Nine million = 9,000
2019-10-24 | IRIS Menu #6 | High |  |  | If I add a workshop, it does not appear added in "Workshop Schedule".
2019-10-24 | IRIS Menu #12.2 | High |  |  | If I add a workshop, it does not appear added in the workshop list
2019-10-24 | IRIS Menu #12.2 | Medium |  |  | Can edit a workshop by clicking on the "New Record" button
2019-10-24 | IRIS Menu #12.2 | Medium |  |  | There is no way to delete a workshop
2019-10-24 | IRIS Menu #2 | Medium |  |  | Can not enter description for an affiliated organization. Gives dropdown selection list of manager, user and administrator.
2019-10-24 | IRIS Menu #2 | Medium |  |  | Once an affiliated organization is created, I can go back in and enter a proper description
2019-10-24 | IRIS Menu #2 | Medium |  |  | The clear button does not clear the list of affiliated organizations.
2019-10-24 | IRIS Menu #2 | Low |  |  | A cell phone is required to add an affiliated organization. This should be the work phone.
2019-10-24 | IRIS Menu #2 | Low |  |  | Affiliated organization creation. State should default to Florida.
2019-10-24 | IRIS Menu #2 | Medium |  |  | Fax phone is not validated numeric
2019-10-24 | IRIS Menu #2 | Medium |  |  | Cell phone is not validated for 10 digits
2019-10-24 | IRIS Menu #2 | Medium |  |  | Work phone is not validated for 10 digits
2019-10-24 | IRIS Menu #2 | Medium |  |  | Fax phone is not validated for 10 digits.
2019-10-24 | IRIS Menu #2 | Medium |  |  | Email is not validated.
2019-10-24 | IRIS Menu #2 | Medium |  |  | Email is not validated for a period '.'
2019-10-24 | IRIS Menu #2 | Medium |  |  | Email is not validated for an asterik '@'
2019-10-24 | IRIS Menu #2 | Medium |  |  | Once a contractual agreement is entered, the start and end dates can be deleted.
2019-10-24 | IRIS Menu #2 | Low |  |  | Can not delete a contract.
2019-10-24 | IRIS Menu #3 | Low |  |  | If the workshop field is cleared, and a search done, it is not as if the filters are cleared, although it looks like it should work as if the filters were cleared.
2019-10-24 | IRIS Menu #3 | Low |  |  | When adding new personnel, the save button is on the right of the screen. The save button should be at the bottom of the screen along with the close button.
2019-10-24 | IRIS Menu #3 | Low |  |  | For existing personnel, the email button is on the right of the screen. The email button should be at the bottom of the screen along with the close button.
2019-10-24 | IRIS Menu #3 | Low |  |  | The personnel record window should open up centered in the window.
2019-10-24 | IRIS Menu #3 | Low |  |  | Gender has the option "other"
2019-10-24 | IRIS Menu #3 | Low |  |  | When creating no error checking for valid email
2019-10-24 | IRIS Menu #3 | Low |  |  | When creating email not validated for period "."
2019-10-24 | IRIS Menu #3 | Low |  |  | When creating email not validated for asterik "@"
2019-10-24 | IRIS Menu #3 | Low |  |  | When creating does not check for valid cell phone number
2019-10-24 | IRIS Menu #3 | Low |  |  | In the tab "Training of Interest", the column heading "Interest in getting training" should have the capitalization "Interested in Getting Training"
2019-10-24 | IRIS Menu #3 | Low |  |  | For standardization, each certification in the Certification tab should have the edit icon, not a button with the word edit.
2019-10-31 | IRIS Menu #3 | Low |  |  | Personnel window does not open centered in screen
2019-10-31 | IRIS Menu #3 | High |  |  | Can create more than 1 personnel with same name. Needs significant other required identifier, like phone# To be part of key
2019-10-31 | IRIS Menu #3 | Low |  |  | Hint "Workshop" should read "Certification"
2019-10-31 | IRIS Menu #3 | Low |  |  | Timeout logs out without giving a notice. Just get an exception when trying to log in.
2019-10-31 | IRIS Menu #3, Demograhpics tab | Medium |  |  | zip code does not check for numeric
2019-10-31 | IRIS Menu #3, Demograhpics tab | Medium |  |  | can not enter a language not creole, english, spanish
2019-10-31 | IRIS Menu #3, Demograhpics tab | Medium |  |  | gender other inappropriate
2019-10-31 | IRIS Menu #3, Affiliations tab | Medium |  |  | can not delete an affiliation
2019-10-31 | IRIS Menu #3, Affiliations tab | Medium |  |  | hint is previous affilation. Should say "Affiliation"
2019-10-31 | IRIS Menu #3, Interested in Getting Training tabs | Low |  |  | column title should be capitalized "Interested in Getting Training" the "G" of getting and the "T" of training
2019-10-31 | IRIS Menu #3, Interested in Getting Training tabs | Low |  |  | an entered interest in training, displays shifted to the right of the column headings
2019-10-31 | IRIS Menu #3, Certifications tab | Medium |  |  | required fields not specified
2019-10-31 | IRIS Menu #3, Certifications tab | Medium |  |  | certification can be a future date
2019-10-31 | IRIS Menu #3, Certifications tab | Low |  |  | Bad UI "Last workshop should be updated by the system" message Above "Last Workshop" column heading change column heading to "Last Workshop Given" followed by an asterisk with a subtext "*Auto-completed by system."
2019-10-31 | IRIS Menu #3, Personnel, Emergency Contact tab | Low |  |  | Can add any field. Name not required
2019-10-31 | IRIS Menu #3, Personnel, Emergency Contact tab | Low |  |  | work phone not validated numeric
2019-10-31 | IRIS Menu #3, Personnel, Emergency Contact tab | Low |  |  | home phone not validated numeric
2019-10-31 | IRIS Menu #3, Personnel, Emergency Contact tab | Low |  |  | cell phone not validated numeric
2019-10-31 | IRIS Menu #3, Personnel, Emergency Contact tab |  |  |  | *** unidentified error. Multiple relationships. Cause unknown. Couldn't duplicate
2019-10-31 | IRIS Menu #3, Personnel, Alert tab | Medium |  |  | can enter an alert without a date
2019-10-31 | IRIS Menu #3, Personnel, Alert tab | Medium |  |  | can not delete an alert
2019-10-31 | IRIS Menu #3, Personnel, Contract tab | Medium |  |  | a contract can be entered without a rate
2019-10-31 | IRIS Menu #3, Personnel, Contract tab | Medium |  |  | when adding a contract, the start & end dates are not recorded
2019-10-31 | IRIS Menu #3, Personnel, Contract tab | Low |  |  | Bad UI When a contract is added, in the left margin it says "Independent Agreement"
2019-11-06 | IRIS Menu #4, Client/Prospects, Basic tab | Low |  |  | Hint for DOB. Grammar error. Should read: "Partial DOB will be considered as empty during for a search."
2019-11-06 | IRIS Menu #4, Client/Prospects, Basic tab | Medium |  |  | Mail icon on main screen does not permit mass mailing. E.g. Can not mail to everyone listed from a search.
2019-11-06 | IRIS Menu #4, Client/Prospects, Basic tab | Medium |  |  | This is another category besides client or prospects. Because 'All' lists more than than clients & prospects together.
2019-10-31 | IRIS Menu #4, Client/Prospects, Basic tab | Low |  |  | Conformity: Should be titled "Demographics"
2019-10-31 | IRIS Menu #4, Client/Prospects, Basic tab | Low |  |  | Gender has choice of "other". Ridiculous. Remove.
2019-10-31 | IRIS Menu #4, Client/Prospects, Basic tab | Low |  |  | Cell phone, Home phone & Work phone should be grouped together.
2019-10-31 | IRIS Menu #4, Client/Prospects, Basic tab | Low |  |  | When creating no error checking for valid email
2019-10-31 | IRIS Menu #4, Client/Prospects, Basic tab | Low |  |  | When creating email not validated for period "."
2019-10-31 | IRIS Menu #4, Client/Prospects, Basic tab | Low |  |  | When creating email not validated for asterik "@"
2019-10-31 | IRIS Menu #4, Client/Prospects, Emergency Contact tab | Low |  |  | does not have a work phone number
2019-10-31 | IRIS Menu #4, Client/Prospects, Emergency Contact tab | Low |  |  | does not have a cell phone number
2019-10-31 | IRIS Menu #4, Client/Prospects, Emergency Contact tab | Medium |  |  | can save an empty record with just relationship
2019-10-31 | IRIS Menu #4, Client/Prospects, Emergency Contact tab | Medium |  |  | can save emergency contact w/o a relationship
2019-10-31 | IRIS Menu #4, Client/Prospects, Emergency Contact tab | Medium |  |  | emergency contact does not have first name
2019-10-31 | IRIS Menu #4, Client/Prospects, Emergency Contact tab | Medium |  |  | emergency contact does not have middle name
2019-10-31 | IRIS Menu #4, Client/Prospects, Emergency Contact tab | Medium |  |  | emergency contact does not have last name
2019-11-06 | IRIS Menu #4, Client/Prospects, Emergency Contact tab | Medium |  |  | No error checking for State. Can enter anything.
2019-11-06 | IRIS Menu #4, Client/Prospects, Emergency Contact tab | Medium |  |  | City field as displayed is too small. Should display at least 15 characters.
2019-10-31 | IRIS Menu #4, Client/Prospects, Chronic Conditions tab | Medium |  |  | Can enter cancer information even if cancer is not selected
2019-10-31 | IRIS Menu #4, Client/Prospects, Chronic Conditions tab | Medium |  |  | Where is cancer information visible? Not displayed
2019-10-31 | IRIS Menu #4, Client/Prospects, Chronic Conditions tab | Medium |  |  | Other conditions not recorded or displayed.
2019-11-06 | IRIS Menu #4, Client/Prospects, Workshop of Interest tab | Medium |  |  | Can enter a "Date of Interest" prior to today's date.
2019-11-06 | IRIS Menu #5, Workshop Sites | Low |  |  | Conformity. Title should read "Workshop Sites"
2019-11-06 | IRIS Menu #5, Workshop Sites | Low |  |  | Site name search does not match first 3 letters. Fix to search by at least 3 letters or remove message.
2019-11-06 | IRIS Menu #5, Workshop Sites | Low |  |  | Contact searches by first name
2019-11-06 | IRIS Menu #5, Workshop Sites | Low |  |  | No error checking for State
2019-11-06 | IRIS Menu #5, Workshop Sites | Low |  |  | State only displays to characters
2019-11-06 | IRIS Menu #5, Workshop Sites | Low |  |  | No dropdown selection list for State.
2019-11-06 | IRIS Menu #5, Workshop Sites | Low |  |  | For Primary Contact: When creating no error checking for valid email
2019-11-06 | IRIS Menu #5, Workshop Sites | Low |  |  | For Primary Contact: When creating email not validated for period "."
2019-11-06 | IRIS Menu #5, Workshop Sites | Low |  |  | For Primary Contact: When creating email not validated for asterik "@"
2019-11-06 | IRIS Menu #5, Workshop Sites | Low |  |  | For Primary Contact: When creating does not check for valid cell phone number
2019-11-06 | IRIS Menu #5, Workshop Sites | Low |  |  | For Secondary Contact: When creating no error checking for valid email
2019-11-06 | IRIS Menu #5, Workshop Sites | Low |  |  | For Secondary Contact: When creating email not validated for period "."
2019-11-06 | IRIS Menu #5, Workshop Sites | Low |  |  | For Secondary Contact: When creating email not validated for asterik "@"
2019-11-06 | IRIS Menu #5, Workshop Sites | Low |  |  | For Secondary Contact: When creating does not check for valid cell phone number
2019-11-06 | IRIS Menu #5, Workshop Sites | Medium |  |  | For Maximum Occupancy. Non-numeric entry gives "validation error" without explanation. An explanation and citing the field, with a red border, to indicate error, should be done.
2019-11-06 | IRIS Menu #5, Workshop Sites | Low |  |  | The site type, "Clinics", in the dropdown list, should read "Clinic" -- no 's'
2019-10-31 | IRIS Menu #6, Workshop Schedule, Personnel tab | High |  |  | workshop needs a master to be created and, the master can not be deleted but the master can lose his certification w/o an alert
2019-11-06 | IRIS Menu #6, Workshop Schedule, main window | Low |  |  | Conformity. When opening a workshop schedule record, the window should have the title "Workshop Schedule" not "Workshop"
2019-11-06 | IRIS Menu #6, Workshop Schedule, entry screen | Medium |  |  | Can create a workshop schedule with a start date before today's date.
2019-11-06 | IRIS Menu #6, Workshop Schedule, entry screen | Medium |  |  | Can create a workshop schedule with an end date before today's date.
2019-11-06 | IRIS Menu #6, Workshop Schedule, entry screen | High |  |  | Can reset status from Completed to Active or Canceled. Should be able to reset the status once completed or cancelled.
2019-11-06 | IRIS Menu #6, Workshop Schedule, entry screen | Medium |  |  | If a new workshop schedule is made, then, you must exit the workshop schedule function in order to see the "Sessions" and "Personnel" tabs.
2019-11-06 | IRIS Menu #6, Workshop Schedule, entry screen | Medium |  |  | MOU can be checked when entering a Workshop Schedule but, is not displayed when viewing a workshop schedule.
| DESIGN ISSUES |  |  |  | should have tablet version to enter data at a workshop
should have only 4 users -- admin, manager, coordinator, coach
manager - should have menu options: funding, affiliated, personnel, clients, workshop sites, schedule, activity, surveys, new setup, reports.
manager should not have access to administration menu option
data coordinator should have all manager functions except funding
coach should have the functions: personnel, clients, workshop schedule, activity schedule, surveys
coach should not be allowed to make changes to the personnel records
coach should be able to enter new clients
coach should not be allowed to create surveys
coach should be allowed to enter data into a survey
coach should not be allowed to access survey setup
activities should have a create/update/delete window
activities should not be hardcoded
should be able to delete workshops
if a survey has been entered for a workshop, then, the workshop can not be deleted
there is only one kind of contract type: MOU
should be able to delete contract type
units in contractual agreement is deprecated -- remove
price/unit in contractual agreement is deprecated -- remove
should be able to delete contracts
MOU is always required
certification for personnnel should automatically update, if giving a class
personnel near the city where a workshop is being given, should automatically be notified of a class, requesting, if they want to teach this class