## Sheet1
Date Reported	Module	Severity / Low/Medium/High / Cosmetic / Security errors have a severity of high.	Fix Planned Y/N	Fix Date	Description

10/10/2019	IRIS Menu #10	Cosmetic			Capitalize "setup" to "Setup" for consistancy
10/10/2019	IRIS Menu #11	Cosmetic			Capitalize "setup" to "Setup" for consistancy
10/10/2019	IRIS Menu #10	Cosmetic			Change "Survey's setup" to "Survey Setup"
10/10/2019	IRIS Menu #10.2	Cosmetic			Change "Survey's Builder" to "Survey Builder"
10/10/2019	IRIS Top Level Menu Bar	High			Right arrow to exit, exits. But, appears to re-enter the system by simply clicking on the browser back arrow. / Functions won't work but, you get the home page without signing in.
10/10/2019	IRIS Top Level Menu Bar	High			Home icon exits. But, appears to re-enter the system by simply clicking on the browser back arrow. / Functions won't work but, you get the home page without signing in.
10/10/2019	IRIS Home Page	Low			There is a help file, titled "User Manual." It does not appear valid. Is it valid? Or partially valid?
10/10/2019	IRIS Menu #5	Cosmetic			Workshop Sites detail entry screen should have a title like all the other detail entry screens. Standardization error.
10/10/2019	IRIS Menu #5	Cosmetic			Workshop Sites screen should have a title "Workshop Sites" matching the menu title like all the other detail entry screens. / Standardization error.
10/17/2019	IRIS Login	High			Password reset emails the user's password in the clear. / It would be safer to simply ask the user to create a new password.
10/17/2019	IRIS Menu #12.4	Cosmetic			When requesting a forgotten password, the alert box stating an email has been sent, opens up on the top of the screen. / The message box should open on top of and centered in the windows already open.
10/17/2019	IRIS Login	Cosmetic			Spelling error. The word "again" is mispelled "againg"
10/17/2019	IRIS Menu #12.4	Cosmetic			When making a change to a user, if there is an issue a message box opens up on the top of the screen. / The message box should open above and centered in the windows already open.
10/17/2019	IRIS Menu #12.4	Cosmetic			When adding a user, upon completion, a message box opens up to the top left of the screen. / The message box should open above and centered in the windows already open.
10/17/2019	IRIS Menu #12.4	High			If I can't create users in different agencies, then why can I see them?
10/17/2019	IRIS Menu #12.4	High			Can create a user without a password

10/17/2019	IRIS Menu #12.4	Unknown			Can not delete a user. The system may want an unalterable history.
10/17/2019	IRIS Menu #12.4	High			Can erase the password from a user's profile and save it successfully.
10/17/2019	IRIS Menu #12.4	High			Can erase the first name from a user's profile and save it successfully.
10/17/2019	IRIS Menu #12.4	High			Can erase the last name from a user's profile and save it successfully.
10/17/2019	IRIS Menu #12.4	High			Can erase the email from a user's profile and save it successfully.
10/17/2019	IRIS Menu #12.4	Low			If an incorrectly formatted email is entered, a message box appears on the top of the screen. / The message box should open on top of and centered in the windows already open.
10/17/2019	IRIS Menu #12.4	Medium			An email is not required to have an extenstion. Ex. ".com"
10/17/2019	IRIS Menu #12.4	Unknown			Can create two users with the same email. This may be acceptable for couples.
10/17/2019	IRIS Menu #12.4	High			Two users can have the same first and last name.
10/17/2019	IRIS Menu #12.4	High			Can create duplicate users

10/17/2019	IRIS Menu #12.4	High			Can erase the password from a coordinator 's profile and save it successfully.
10/17/2019	IRIS Menu #12.4	High			Can erase the first name from a coordinator 's profile and save it successfully.
10/17/2019	IRIS Menu #12.4	High			Can erase the last name from a coordinator 's profile and save it successfully.
10/17/2019	IRIS Menu #12.4	High			Can erase the email from a coordinator 's profile and save it successfully.
10/17/2019	IRIS Menu #12.4	Low			If an incorrectly formatted email is entered, a message box appears on the top of the screen. / The message box should open on top of and centered in the windows already open.
10/17/2019	IRIS Menu #12.4	Medium			An email is not required to have an extenstion. Ex. ".com"
10/17/2019	IRIS Menu #12.4	Unknown			Can create two coordinator s with the same email. This may be acceptable for couples.
10/17/2019	IRIS Menu #12.4	High			Two coordinator s can have the same first and last name.
10/17/2019	IRIS Menu #12.4	High			Can create duplicate coordinator s
10/17/2019	IRIS Menu #12.4	Cosmetic			When adding a coordinator , upon completion, a message box opens up to the top left of the screen. / The message box should open above and centered in the windows already open.

10/17/2019	IRIS Menu #12.4	High			Can erase the password from a manager's profile and save it successfully.
10/17/2019	IRIS Menu #12.4	High			Can erase the first name from a manager's profile and save it successfully.
10/17/2019	IRIS Menu #12.4	High			Can erase the last name from a manager's profile and save it successfully.
10/17/2019	IRIS Menu #12.4	High			Can erase the email from a manager's profile and save it successfully.
10/17/2019	IRIS Menu #12.4	Low			If an incorrectly formatted email is entered, a message box appears on the top of the screen. / The message box should open on top of and centered in the windows already open.
10/17/2019	IRIS Menu #12.4	Medium			An email is not required to have an extenstion. Ex. ".com"
10/17/2019	IRIS Menu #12.4	Unknown			Can create two managers with the same email. This may be acceptable for couples.
10/17/2019	IRIS Menu #12.4	High			Two managers can have the same first and last name.
10/17/2019	IRIS Menu #12.4	High			Can create duplicate managers
10/17/2019	IRIS Menu #12.4	Cosmetic			When adding a manager, upon completion, a message box opens up to the top left of the screen. / The message box should open above and centered in the windows already open.

10/17/2019	IRIS Menu #12.3	High			The roles do not seem to have any effect. Access to a function is permitted even if not allowed.
10/17/2019	IRIS Menu #12.3	High			The roles do not seem to have any effect. Access to a function is permitted even if not allowed. Data can displayed.
10/17/2019	IRIS Menu #12.3	High			The roles do not seem to have any effect. Any user can escalate rights even if they do not have access to administration.
10/17/2019	IRIS Menu #12.3	Medium			When a new user role is created, it does not appear in the table of user roles, even if filters are cleared. / One must exit the "User Roles" function and re-enter the function for the new role to appear.
10/17/2019	IRIS Menu #12.3	Medium			If adding a role and no agency is selected, the message "Data Saved" appears / and it looks like the new role was created. But, it is not in the table. / If it is entered as garbage into the file, I can not see.

10/17/2019	IRIS Menu #12.1	High			Duplicate agencies with same name and region allowed.

10/24/2019	IRIS Menu #1	Medium			Can not enter a funding source in the textbox for funding source, to do a search
10/24/2019	IRIS Menu #1	Medium			Can not create a funding source once any action has been taken within the funding source window. / Can only enter a new funding source when first entering the funding source window.
10/24/2019	IRIS Menu #1	Medium			Budget amount zeroes out if entered with funding source creation.
10/24/2019	IRIS Menu #1	Medium			Budget amount must be at least one dollar
10/24/2019	IRIS Menu #1	Medium			Budget amount can not have pennies.
10/24/2019	IRIS Menu #1	Medium			Budget amount limited to 999,999.00
10/24/2019	IRIS Menu #1	Medium			If a budget of one million is entered, the amount is converted to thousands. / One million = 1,000 Nine million = 9,000

10/24/2019	IRIS Menu #6	High			If I add a workshop, it does not appear added in "Workshop Schedule".
10/24/2019	IRIS Menu #12.2	High			If I add a workshop, it does not appear added in the workshop list
10/24/2019	IRIS Menu #12.2	Medium			Can edit a workshop by clicking on the "New Record" button
10/24/2019	IRIS Menu #12.2	Medium			There is no way to delete a workshop

10/24/2019	IRIS Menu #2	Medium			Can not enter description for an affiliated organization. / Gives dropdown selection list of manager, user and administrator.
10/24/2019	IRIS Menu #2	Medium			Once an affiliated organization is created, I can go back in and enter a proper description
10/24/2019	IRIS Menu #2	Medium			The clear button does not clear the list of affiliated organizations.
10/24/2019	IRIS Menu #2	Low			A cell phone is required to add an affiliated organization. This should be the work phone.
10/24/2019	IRIS Menu #2	Low			Affiliated organization creation. State should default to Florida.
10/24/2019	IRIS Menu #2	Medium			Fax phone is not validated numeric
10/24/2019	IRIS Menu #2	Medium			Cell phone is not validated for 10 digits
10/24/2019	IRIS Menu #2	Medium			Work phone is not validated for 10 digits
10/24/2019	IRIS Menu #2	Medium			Fax phone is not validated for 10 digits.
10/24/2019	IRIS Menu #2	Medium			Email is not validated.
10/24/2019	IRIS Menu #2	Medium			Email is not validated for a period '.'
10/24/2019	IRIS Menu #2	Medium			Email is not validated for an asterik '@'
10/24/2019	IRIS Menu #2	Medium			Once a contractual agreement is entered, the start and end dates can be deleted.
10/24/2019	IRIS Menu #2	Low			Can not delete a contract.

10/24/2019	IRIS Menu #3	Low			If the workshop field is cleared, and a search done, it is not as if the filters are cleared, / although it looks like it should work as if the filters were cleared.If the workshop field is cleared, and a search done, it is not as if the filters are cleared, / although it looks like it should work as if the filters were cleared.If the workshop field is cleared, and a search done, it is not as if the filters are cleared, / although it looks like it should work as if the filters were cleared.
10/24/2019	IRIS Menu #3	Low			When adding new personnel, the save button is on the right of the screen. / The save button should be at the bottom of the screen along with the close button.When adding new personnel, the save button is on the right of the screen. / The save button should be at the bottom of the screen along with the close button.When adding new personnel, the save button is on the right of the screen. / The save button should be at the bottom of the screen along with the close button.
10/24/2019	IRIS Menu #3	Low			For existing personnel, the email button is on the right of the screen. / The email button should be at the bottom of the screen along with the close button.For existing personnel, the email button is on the right of the screen. / The email button should be at the bottom of the screen along with the close button.For existing personnel, the email button is on the right of the screen. / The email button should be at the bottom of the screen along with the close button.
10/24/2019	IRIS Menu #3	Low			The personnel record window should open up centered in the window.
10/24/2019	IRIS Menu #3	Low			Gender has the option "other"
10/24/2019	IRIS Menu #3	Low			When creating no error checking for valid email
10/24/2019	IRIS Menu #3	Low			When creating email not validated for period "."
10/24/2019	IRIS Menu #3	Low			When creating email not validated for asterik "@"
10/24/2019	IRIS Menu #3	Low			When creating does not check for valid cell phone number
10/24/2019	IRIS Menu #3	Low			In the tab "Training of Interest", / the column heading "Interest in getting training" / should have the capitalization "Interested in Getting Training"In the tab "Training of Interest", / the column heading "Interest in getting training" / should have the capitalization "Interested in Getting Training"In the tab "Training of Interest", / the column heading "Interest in getting training" / should have the capitalization "Interested in Getting Training"
10/24/2019	IRIS Menu #3	Low			For standardization, each certification in the Certification tab / should have the edit icon, not a button with the word edit.For standardization, each certification in the Certification tab / should have the edit icon, not a button with the word edit.For standardization, each certification in the Certification tab / should have the edit icon, not a button with the word edit.
10/31/2019	IRIS Menu #3	Low			Personnel window does not open centered in screen
10/31/2019	IRIS Menu #3	High			Can create more than 1 personnel with same name. / Needs significant other required identifier, like phone# / To be part of keyCan create more than 1 personnel with same name. / Needs significant other required identifier, like phone# / To be part of keyCan create more than 1 personnel with same name. / Needs significant other required identifier, like phone# / To be part of key
10/31/2019	IRIS Menu #3	Low			Hint "Workshop" should read "Certification"
10/31/2019	IRIS Menu #3	Low			Timeout logs out without giving a notice. Just get an exception when trying to log in.
10/31/2019	IRIS Menu #3, Demograhpics tab	Medium			zip code does not check for numeric
10/31/2019	IRIS Menu #3, Demograhpics tab	Medium			can not enter a language not creole, english, spanish
10/31/2019	IRIS Menu #3, Demograhpics tab	Medium			gender other inappropriate
10/31/2019	IRIS Menu #3, Affiliations tab	Medium			can not delete an affiliation
10/31/2019	IRIS Menu #3, Affiliations tab	Medium			hint is previous affilation. Should say "Affiliation"
10/31/2019	IRIS Menu #3, Interested in Getting Training tabs	Low			column title should be capitalized "Interested in Getting Training" / the "G" of getting and the "T" of trainingcolumn title should be capitalized "Interested in Getting Training" / the "G" of getting and the "T" of training
10/31/2019	IRIS Menu #3, Interested in Getting Training tabs	Low			an entered interest in training, displays shifted to the right of the column headings
10/31/2019	IRIS Menu #3, Certifications tab	Medium			required fields not specified
10/31/2019	IRIS Menu #3, Certifications tab	Medium			certification can be a future date
10/31/2019	IRIS Menu #3, Certifications tab	Low			Bad UI / "Last workshop should be updated by the system" message / Above "Last Workshop" column heading / change column heading to "Last Workshop Given" followed by an asterisk / with a subtext "*Auto-completed by system."Bad UI / "Last workshop should be updated by the system" message / Above "Last Workshop" column heading / change column heading to "Last Workshop Given" followed by an asterisk / with a subtext "*Auto-completed by system."
10/31/2019	IRIS Menu #3, Personnel, Emergency Contact tab	Low			Can add any field. Name not required
10/31/2019	IRIS Menu #3, Personnel, Emergency Contact tab	Low			work phone not validated numeric
10/31/2019	IRIS Menu #3, Personnel, Emergency Contact tab	Low			home phone not validated numeric
10/31/2019	IRIS Menu #3, Personnel, Emergency Contact tab	Low			cell phone not validated numeric
10/31/2019	IRIS Menu #3, Personnel, Emergency Contact tab				*** unidentified error. Multiple relationships. Cause unknown. / Couldn't duplicate*** unidentified error. Multiple relationships. Cause unknown. / Couldn't duplicate
10/31/2019	IRIS Menu #3, Personnel, Alert tab	Medium			can enter an alert without a date
10/31/2019	IRIS Menu #3, Personnel, Alert tab	Medium			can not delete an alert
10/31/2019	IRIS Menu #3, Personnel, Contract tab	Medium			a contract can be entered without a rate
10/31/2019	IRIS Menu #3, Personnel, Contract tab	Medium			when adding a contract, the start & end dates are not recorded
10/31/2019	IRIS Menu #3, Personnel, Contract tab	Low			Bad UI / When a contract is added, in the left margin / it says "Independent Agreement"

11/6/2019	IRIS Menu #4, Client/Prospects, Basic tab	Low			Hint for DOB. Grammar error. Should read: / "Partial DOB will be considered as empty during for a search."
11/6/2019	IRIS Menu #4, Client/Prospects, Basic tab	Medium			Mail icon on main screen does not permit mass mailing. / E.g. Can not mail to everyone listed from a search.
11/6/2019	IRIS Menu #4, Client/Prospects, Basic tab	Medium			This is another category besides client or prospects. / Because 'All' lists more than than clients & prospects together.

10/31/2019	IRIS Menu #4, Client/Prospects, Basic tab	Low			Conformity: Should be titled "Demographics"
10/31/2019	IRIS Menu #4, Client/Prospects, Basic tab	Low			Gender has choice of "other". / Ridiculous. Remove.
10/31/2019	IRIS Menu #4, Client/Prospects, Basic tab	Low			Cell phone, Home phone & Work phone should be grouped together.
10/31/2019	IRIS Menu #4, Client/Prospects, Basic tab	Low			When creating no error checking for valid email
10/31/2019	IRIS Menu #4, Client/Prospects, Basic tab	Low			When creating email not validated for period "."
10/31/2019	IRIS Menu #4, Client/Prospects, Basic tab	Low			When creating email not validated for asterik "@"

10/31/2019	IRIS Menu #4, Client/Prospects, Emergency Contact tab	Low			does not have a work phone number
10/31/2019	IRIS Menu #4, Client/Prospects, Emergency Contact tab	Low			does not have a cell phone number
10/31/2019	IRIS Menu #4, Client/Prospects, Emergency Contact tab	Medium			can save an empty record with just relationship
10/31/2019	IRIS Menu #4, Client/Prospects, Emergency Contact tab	Medium			can save emergency contact w/o a relationship
10/31/2019	IRIS Menu #4, Client/Prospects, Emergency Contact tab	Medium			emergency contact does not have first name
10/31/2019	IRIS Menu #4, Client/Prospects, Emergency Contact tab	Medium			emergency contact does not have middle name
10/31/2019	IRIS Menu #4, Client/Prospects, Emergency Contact tab	Medium			emergency contact does not have last name
11/6/2019	IRIS Menu #4, Client/Prospects, Emergency Contact tab	Medium			No error checking for State. Can enter anything.
11/6/2019	IRIS Menu #4, Client/Prospects, Emergency Contact tab	Medium			City field as displayed is too small. Should display at least 15 characters.
10/31/2019	IRIS Menu #4, Client/Prospects, Chronic Conditions tab	Medium			Can enter cancer information even if cancer is not selected
10/31/2019	IRIS Menu #4, Client/Prospects, Chronic Conditions tab	Medium			Where is cancer information visible? Not displayed
10/31/2019	IRIS Menu #4, Client/Prospects, Chronic Conditions tab	Medium			Other conditions not recorded or displayed.
11/6/2019	IRIS Menu #4, Client/Prospects, Workshop of Interest tab	Medium			Can enter a "Date of Interest" prior to today's date.

11/6/2019	IRIS Menu #5, Workshop Sites	Low			Conformity. Title should read "Workshop Sites"
11/6/2019	IRIS Menu #5, Workshop Sites	Low			Site name search does not match first 3 letters. / Fix to search by at least 3 letters or remove message.
11/6/2019	IRIS Menu #5, Workshop Sites	Low			Contact searches by first name
11/6/2019	IRIS Menu #5, Workshop Sites	Low			No error checking for State
11/6/2019	IRIS Menu #5, Workshop Sites	Low			State only displays to characters
11/6/2019	IRIS Menu #5, Workshop Sites	Low			No dropdown selection list for State.
11/6/2019	IRIS Menu #5, Workshop Sites	Low			For Primary Contact: When creating no error checking for valid email
11/6/2019	IRIS Menu #5, Workshop Sites	Low			For Primary Contact: When creating email not validated for period "."
11/6/2019	IRIS Menu #5, Workshop Sites	Low			For Primary Contact: When creating email not validated for asterik "@"
11/6/2019	IRIS Menu #5, Workshop Sites	Low			For Primary Contact: When creating does not check for valid cell phone number
11/6/2019	IRIS Menu #5, Workshop Sites	Low			For Secondary Contact: When creating no error checking for valid email
11/6/2019	IRIS Menu #5, Workshop Sites	Low			For Secondary Contact: When creating email not validated for period "."
11/6/2019	IRIS Menu #5, Workshop Sites	Low			For Secondary Contact: When creating email not validated for asterik "@"
11/6/2019	IRIS Menu #5, Workshop Sites	Low			For Secondary Contact: When creating does not check for valid cell phone number
11/6/2019	IRIS Menu #5, Workshop Sites	Medium			For Maximum Occupancy. Non-numeric entry gives "validation error" without explanation. / An explanation and citing the field, with a red border, to indicate error, should be done.
11/6/2019	IRIS Menu #5, Workshop Sites	Low			The site type, "Clinics", in the dropdown list, should read "Clinic" -- no 's'

10/31/2019	IRIS Menu #6, Workshop Schedule, Personnel tab	High			workshop needs a master to be created / and, the master can not be deleted / but the master can lose his certification w/o an alert
11/6/2019	IRIS Menu #6, Workshop Schedule, main window	Low			Conformity. When opening a workshop schedule record, the window should have the title "Workshop Schedule" not "Workshop"
11/6/2019	IRIS Menu #6, Workshop Schedule, entry screen	Medium			Can create a workshop schedule with a start date before today's date.
11/6/2019	IRIS Menu #6, Workshop Schedule, entry screen	Medium			Can create a workshop schedule with an end date before today's date.
11/6/2019	IRIS Menu #6, Workshop Schedule, entry screen	High			Can reset status from Completed to Active or Canceled. / Should be able to reset the status once completed or cancelled.
11/6/2019	IRIS Menu #6, Workshop Schedule, entry screen	Medium			If a new workshop schedule is made, then, you must exit the workshop schedule function in order to see the "Sessions" and "Personnel" tabs.
11/6/2019	IRIS Menu #6, Workshop Schedule, entry screen	Medium			MOU can be checked when entering a Workshop Schedule but, is not displayed when viewing a workshop schedule.

11/25/2019	System Wide	Low			Needs a proper timeout message. Not some cryptic system error.
11/25/2019	System Wide	Medium			Can not access scroll bar for sidebar menu. Disappears on mouse movement
		High			Top of Personnel edit window is not visible on the computer screen. The pattern of occurrence is undefined. It happens “Sometimes.”

	DESIGN ISSUES				should have tablet version to enter data at a workshop
					should have only 4 users -- admin, manager, coordinator, coach
					manager - should have menu options: / funding, affiliated, personnel, clients, workshop sites, schedule, activity, surveys, new setup, reports.
					manager should not have access to administration menu option
					data coordinator should have all manager functions except funding
					coach should have the functions: personnel, clients, workshop schedule, activity schedule, surveys
					coach should not be allowed to make changes to the personnel records
					coach should be able to enter new clients
					coach should not be allowed to create surveys
					coach should be allowed to enter data into a survey
					coach should not be allowed to access survey setup
					activities should have a create/update/delete window
					activities should not be hardcoded
					should be able to delete workshops
					if a survey has been entered for a workshop, then, the workshop can not be deleted
					there is only one kind of contract type: MOU
					should be able to delete contract type
					units in contractual agreement is deprecated -- remove
					price/unit in contractual agreement is deprecated -- remove
					should be able to delete contracts
					MOU is always required
					certification for personnnel should automatically update, if giving a class
					personnel near the city where a workshop is being given, / should automatically be notified of a class, requesting, if they want to teach this class